## HLP
# | HLP Name | Item Description | Track Execution Team | Due Date | Completed Date | Status | Red, Yellow, Green? | Reason for Delay | General Notes
1 | Monorepo Foundation for (highradius_ui_config, highradius_core_ui and highradius_aps_ui) | - Establish a robust monorepo structure with Yarn v4, Node.js 23, and Turborepo. - Standardize developer workflow with Git hooks (Husky, Lint Staged, Commitlint, Commitizen). - Centralize and enforce consistent configurations (TypeScript, ESLint, Prettier, Jest). - Streamline new project/package creation with Turborepo's generation tools. | G4 Devops |  |  | In Progress | Green
2 | Automated Build, Test & Deployment Pipeline (highradius_core_ui and highradius_aps_ui) | - Implement comprehensive CI/CD pipelines (e.g., GitHub Actions) for automated builds, tests, and deployments. - Automate versioning and changelog generation using Semantic Release with Turborepo integration. - Integrate performance monitoring (Lighthouse, bundle analysis) and security scanning into the CI/CD process. | G4 Devops |  |  | In Progress | Green
3 | Unified UI/UX Framework & Documentation (highradius_core_ui and highradius_aps_ui) | - Establish a shared Material UI configuration (`HiRa Theme`) for design consistency. - Develop a core UI component library (`@highradius_core_ui/core`) using Material UI. - Provide dedicated documentation portals for component usage (Storybook) and project-level information (Docusaurus). - Implement accessibility (A11y) and internationalization (i18n) best practices for an inclusive user experience. | G4 Platform |  |  | Not Started | Green
4 | Advanced Data Management & API Layer (highradius_core_ui and highradius_aps_ui) | - Set up a centralized Redux Toolkit store (`@highradius_aps_ui/redux_config`) for state management. - Implement a comprehensive data caching strategy (`@highradius_core_ui/data_cache`) with intelligent invalidation (time-based, DSL-driven, navigation-aware) and background refresh capabilities. - Establish best practices for API client interaction and error handling across applications. | G4 Platform |  |  | Not Started | Green
5 | Core Application Components & Observability Advanced Data Management & API Layer (highradius_core_ui and highradius_aps_ui) | - Develop a feature-rich AG Grid component (`@highradius_core_ui/grid`) for Admin UI, including extensive state caching for user interactions (sorting, filtering, pagination, column width, selection) and API data persistence. - Implement comprehensive observability (error monitoring, structured logging, RUM) across the monorepo for application health and performance insights. | G4 Platform |  |  | In Progress | Green

## 1.1. Monorepo Setup
HLP Track no.
HLP Type | Monorepo Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Initial Turborepo with Monorepo Setup and Codebase Structure Init: Use yarn create-turbo@latest. Yarn v4: packageManager: "yarn@4.x.x" in root package.json, enable workspaces. Node.js 23: Enforce with .nvmrc or volta at root. Structure: apps/ for deployable applications, packages/ for shared code (UI, Redux, utilities, configs, types). |  | Sachidananda Panigrahi
2 | Setup Husky for Git Hooks Purpose: Enforce code quality/commit standards on pre-commit, pre-push, commit-msg. Install: husky as dev dependency (root). Config: "prepare": "husky" script; husky add .husky/<hook-name> "command" |  | Sachidananda Panigrahi
3 | Setup Lint Staged Purpose: Run linters/formatters only on staged files for faster commits. Install: lint-staged as dev dependency (root). Config: lint-staged block in root package.json with file-specific commands. Integration: Called by Husky pre-commit hook. |  | Sachidananda Panigrahi
4 | Setup Commitlint Purpose: Enforce conventional commit messages (feat:, fix:) for changelog automation. Install: @commitlint/cli, @commitlint/config-conventional (root). Config: commitlint.config.js at root. Integration: Called by Husky commit-msg hook. |  | Sachidananda Panigrahi
5 | Setup Commitizen Purpose: Interactive CLI to help developers create conventional commit messages. Install: commitizen, cz-conventional-changelog (root). Config: config.commitizen.path in root package.json. Usage: Add "commit": "cz" script for developers to use. |  | Sachidananda Panigrahi
6 | CI/CD Setup (e.g., GitHub Actions) Version Management: Use semantic-release (with semantic-release-turbo) to automate versioning, changelog, and publishing based on commits. Changelog: Automatically generated by semantic-release. CI Provider: Configure caching for node_modules and .turbo cache; leverage Turborepo's turbo run for parallel tasks. Deployment: Separate CI/CD jobs for deploying individual apps/ to environments. |  | Sachidananda Panigrahi
7 | Performance Monitoring Google Lighthouse: Integrate lighthouse-ci into CI to run audits and fail builds on regressions. React Tooling: webpack-bundle-analyzer for bundle size optimization. Monitor Web Vitals (LCP, FID, CLS) in production. Use React DevTools Profiler locally. Implement code splitting/lazy loading. |  | Sachidananda Panigrahi
8 | Dependency Management with Yarn v4 Plug'n'Play (PnP): Leverage PnP benefits; ensure tool compatibility (yarn dlx @yarnpkg/sdks). --immutable: Use in CI for reproducibility. nmHoistingLimits: Use in .yarnrc.yml if specific tools need hoisted node_modules. workspace:: Use for all internal package dependencies. |  | Sachidananda Panigrahi
9 | Streamlined Package Creation Purpose: Quickly create new apps/ or packages/ workspaces by copying boilerplate from an existing template. This ensures consistency and speeds up development. Tool: Utilize turbo gen workspace --copy <source-package-path> in your terminal. Workflow: Maintain template packages (e.g., a minimal packages/template-ui-lib or apps/template-web-app) which can be copied and customized for new projects, reducing setup time and enforcing monorepo standards. |  | Sachidananda Panigrahi
10 | Build System Configuration (Turborepo Specific) turbo.json Pipeline: Define build, dev, lint, test tasks with dependsOn and outputs for caching. Remote Caching: Set up with Vercel or self-hosted solution to share build caches across environments. |  | Sachidananda Panigrahi
11 | Documentation (Project-Level) Docusaurus: Set up apps/docs for comprehensive project-level documentation, including architecture guides, contribution guidelines, and decision logs. API Docs: Integrate automatically generated API documentation (e.g., using TypeDoc for TypeScript) into the Docusaurus site. |  | Sachidananda Panigrahi

## 1.2.Storybook Setup
HLP Track no.
HLP Type | Storybook Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Create a new project apps/storybook (or @highradius_core_ui/storybook if you use scoped NPM packages) within your monorepo.
2 | Latest Version: Initialize Storybook with its latest stable version within this new project (yarn storybook@latest init).
3 | Publishing: Configure Storybook for static site export (e.g., using build-storybook command) and integrate its deployment into your CI/CD pipeline for continuous publishing to a hosting service (e.g., Netlify, Vercel, GitHub Pages).
4 | Integrate and configure the Storybook project to find and load `.stories.tsx` files from your shared UI component packages, such as `packages/core` for Core components and `packages/grid` for custom AG Grid wrapper components, after these stories have been added to the Storybook project.
5
6
7
8

## 1.3. Docs App Setup
HLP Track no.
HLP Type | Docs App Setup with Next JS and React 19
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Add a new project called @highradius_core_ui/docs_app outside of packages folder and in app folder into the monorepo
2 | Setup Next JS with latest version in this project with React 19
3 | Add relevant all the components like Core components and Grid to the Docs App project and test if evrything works fine
4
5
6
7
8

## 4.Eslint Setup
HLP Track no.
HLP Type | Eslint Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Add a new project called @highradius_core_ui/eslint_config into the monorepo
2 | Setup Eslint:- To use eslint in project setup for code quality and linting
3 | export the config from eslint config project for further use
4
5
6
7
8

## 5. Prettier Setup
HLP Track no.
HLP Type | Prettier Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Add a new project called @highradius_core_ui/prettier_config into the monorepo
2 | Setup Prettier:- To use prettier in project setup for code formatting
3 | export the config from Prettier config project for further use
4
5
6
7
8

## 6. Webpack Setup
HLP Track no.
HLP Type | Webpack Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Add a new project (package) named @highradius_core_ui/webpack_config within the packages/configs directory (e.g., packages/configs/webpack-config-custom).
2 | Export Configuration: Define and export reusable Webpack configuration functions or objects within this package for both development and production builds.
3 | Modular Configs: Create separate configuration files for common loaders, plugins, optimizations, and dev server settings that can be merged or extended by individual apps/ or other packages/.
4 | Consumption: Configure consuming apps/ (e.g., apps/web) to import and use these shared Webpack configurations in their build processes.
5
6
7
8

## 7. Redux Config
HLP Track no.
HLP Type | Redux Toolkit Setup
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Add a new project (package) called @highradius_core_ui/redux_config within the packages/ directory (ideally named packages/core-redux for clarity).
2 | Central Store & Provider Export: Configure the central Redux store (configureStore) within this package and export the Redux Provider component.
3 | Reducer Merging: Implement a strategy (e.g., convention-based file scanning or a dedicated aggregation file) to automatically or semi-automatically merge reducers from feature-specific slices (e.g., authSlice, productSlice from other packages/) into the single root reducer, avoiding direct imports of every slice.
4 | RTK Query Integration: Ensure the createApi instances from RTK Query (whether defined here or imported from other packages) have their reducers merged and middleware included in the central store.
5 | Type Exports: Export RootState and AppDispatch types for strongly typed useSelector and useDispatch hooks in consuming applications.
6
7
8

## 8. Material UI Config
HLP Track no.
HLP Type | Material UI Config
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Add a new package @highradius_core_ui/material_ui_config within packages/configs (e.g., packages/configs/material-ui-config).
2 | MUI Theme Configuration: Set up and export a centralized Material UI theme using createTheme(), defining a consistent design system (typography, spacing, breakpoints, z-index).
Default HiRa Theme: Define and export a specific "HiRa Theme" (your brand's default) with its complete color palette, typography, and component overrides for UI consistency.
3 | Theme Provider Export: Create and export a custom React ThemeProvider component from this package, wrapping Material UI's ThemeProvider to apply the "HiRa Theme" to consuming applications.
4 | Color Palette Export: Define and export a set of consistent COLORS (e.g., primary, secondary, error, success, neutral shades) as an object or enum for easy access across all projects.
5
6
7
8

## 9. Core Components
HLP Track no.
HLP Type | Core Components
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Add a new package called @highradius_core_ui/core (e.g., packages/ui/core) within your monorepo.
2 | MUI Integration & Atomic Components: Import configurations from @highradius_core_ui/material_ui_config. Develop foundational "atomic" UI components (e.g., Button, Input, Checkbox, Typography) using Material UI to ensure consistent UI design. Prioritize onboarding components specifically required for your "User Grid Component" initially.
3 | Export for Reuse: Export all developed core components from this package, making them easily consumable by apps/ and other packages/ across the monorepo for consistent UI implementation.
4 | Storybook Integration: Ensure these core components have accompanying stories in the apps/storybook project for documentation and isolated development.
3
4
5
6
7
8

## 10. Data Caching
HLP Track no.
HLP Type | Data Caching (highradius_aps_ui)
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Add a new package called @highradius_aps_ui/data_cache (e.g., packages/data-cache) within your monorepo. This package will encapsulate core caching logic and Redux integration.
2 | Redux-Based Storage: Utilize Redux (leveraging Redux Toolkit Query's cache if applicable, or custom slices) to store API responses and application-specific data.
3 | Timestamp-Based Expiration: Implement a mechanism to add timestamps to cached data, enabling time-based expiration and stale data revalidation.
4 | Cache Check Middleware/Logic: Develop custom Redux middleware or service logic within this package to intercept data requests, check for existing cached data, and serve it if valid before initiating new API calls.
5 | Dynamic Invalidation Rules: Define and implement robust rules for invalidating cached data. This includes:
6 | DSL Flag-Based Invalidation: Implement logic to listen for specific Domain Specific Language (DSL) flags (e.g., from websocket events, or specific API responses) to trigger refreshes of associated cached data.
7 | Time-Based Expiration: Utilize timestamps and keepUnusedDataFor (for RTK Query) or custom timers for automatic cache expiration.
8 | Manual Triggers: Provide utilities for manual cache invalidation where necessary.
9 | Page Context Management: Add mechanisms to store page-specific context within the Redux Store and maintain it during navigation, ensuring data relevancy.
10 | Navigation-Based Data Refresh: Implement logic to pass previous page IDs/keys to the next page. This reference can be used to intelligently clean or refresh data on the previous page when navigating back or when related data changes.
Background Data Refresh for UX: Enhance user experience by implementing background data refreshes. For example, upon a successful data modification on a detail page (e.g., KVP page), trigger a background refresh of related listing page data (e.g., User Listing page grid data) to ensure immediate consistency without a full page reload for the user.
Robust Error Handling: Implement comprehensive error handling within the API cache middleware/logic, gracefully managing network failures, cache read/write errors, and data inconsistencies.
Comprehensive Dev Testing: Conduct thorough development testing for all possible scenarios, including cache hits, misses, expirations, invalidations (time, DSL, manual), concurrent updates, and the impact on user experience across various navigation flows.

## 11. Core Grid Component
HLP Track no.
HLP Type | Basic or Core Grid Component
HLP Description
Track | Item Description | Dev PDs | Priority | Execution Owner / Item Owner | Dev Owner | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Create a new package called `@highradius_core_ui/grid` (e.g., `packages/grid`) within your monorepo. This will house the reusable AG Grid component.
2 | AG Grid Installation & Theming: Install AG Grid (Community and Enterprise modules as needed) within this package. Integrate `@highradius_core_ui/material_ui_config` to apply HiRa themes, ensuring consistent styling for AG Grid components.
3 | Custom Cell Renderers: Develop and integrate specific display renderers for various data types:
4 | `Boolean Display Renderer`: For optimized rendering of boolean values.
5 | `DateTime Display Renderer`: For consistent date and time formatting.
6 | `Text Display Renderers`: For customized display of text fields, potentially with truncation or tooltips.
7 | Support all the Renderers(Wrapping of text)
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31

## 12. Advanced Grid Component
HLP Track no.
HLP Type | Advance Grid Component with Caching
HLP Description
Track | Item Description | Dev PDs | Priority | Execution Owner / Item Owner | Dev Owner | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Project Creation: Create a new package called `@highradius_aps_ui/grid` (e.g., `packages/grid`) within your monorepo. This will house the reusable AG Grid component.
2 | Install and import Grid package from `@highradius_core_ui/Grid`
3 | DSL Configuration Integration: Implement logic to receive DSL (Domain Specific Language) configurations for the grid (e.g., column definitions, feature flags). Add a transformation layer to convert DSL into AG Grid's readable configuration format if necessary.
4 | V2 Grid Enablement: Add a feature to enable an alternative "V2 Grid" configuration or specific advanced features of AG Grid based on a flag provided by the DSL.
5 | API Integration: Integrate the grid component with your application's API endpoints for data fetching (likely via RTK Query from `packages/data-cache` or `packages/core-redux`).
6 | Core Grid Feature Caching: Implement Redux-based caching of user interactions and grid state for enhanced UX and data persistence across sessions/revisits:
7 | Sort Page Caching: Store and retrieve applied sort configurations.
8 | Search Page Caching: Store and retrieve active global search terms.
9 | Column Search Page Caching: Store and retrieve individual column filter states.
10 | Saved Search Page Caching: Implement storage and retrieval for user-defined "saved search" filters.
11 | Refresh Button Click Caching: Ensure a "Refresh" button clears relevant data caches and triggers a data refetch.
12 | Feature Integration & Caching:
13 | Export Feature: Integrate AG Grid's export functionality (CSV/Excel). Implement logic to clone/enhance this feature to work seamlessly with cached data or trigger fresh data export if required.
14 | Pagination Features: Integrate and enhance AG Grid's pagination features. Store and retrieve user-selected page size and current page number in Redux.
15 | Bulk Action Feature: Implement and integrate a bulk action feature (e.g., select multiple rows for an action). Store and retrieve the state of selected rows in Redux.
16 | Parametric Search: Integrate a parametric search (faceted search) into the Grid, ensuring that applied parametric filters are stored in Redux and retrieved for caching.
17 | API Data Caching:
18 | Store API data fetched for the Grid component in the Redux store (cache).
19 | Retrieve cached API data for initial grid rendering and when the user revisits the Grid component (e.g., returning from a detail page).
20 | User Interaction Caching (Redux-backed Persistence):
21 | Column Width: Store user-initiated column width changes in Redux. Retrieve these cached widths when the user revisits the grid.
22 | Column Filter: Store user-applied column filter states in Redux. Retrieve cached filter states when the user revisits the grid.
23 | Column Sorting: Store user-applied column sorting configurations in Redux. Retrieve cached sorting configurations when the user revisits the grid.
24 | Pagination State: Store user-selected pagination (page size, current page) in Redux. Retrieve this cached pagination state when the user revisits the grid.
25 | Row Selection: Store the state of user-selected rows in Redux. Retrieve cached row selections when the user revisits the grid.
26 | Applied Saved Filter: Store the ID or configuration of the currently applied saved filter in Redux. Retrieve this state when the user revisits the grid.
27
28
29
30
31

## Copy of 2.User Grid Component (hidden)
HLP Track no. | Grid Component Caching for Admin UI User Listing
HLP Type
HLP Description
Track | Item Description | Dev PDs | Priority | Execution Owner / Item Owner | Dev Owner | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Implement the Grid from Base component and create a Grid v2 component in UX Framework with Static Data | 2
2 | Add feature to enable v2 grid with a flag from DSL | 1
3 | Integrate API | 1
4 | Add Boolean Display Renderer for page caching | 1
5 | Add DateTime Display Renderer for page caching | 1
6 | Add Text Display Renderers for page caching | 1
7 | Add sort page caching feature | 1
8 | Add search page caching feature | 2
9 | Add column search page caching feature | 2
10 | Add saved search page caching feature | 5
11 | Add refresh button click page caching feature | 1
12 | Add or clone export feature for page caching | 1
13 | Add or clone Pagination features for page caching | 3
14 | Add or clone Bulk Action Feature for page caching | 2
15 | Add or clone and integrate paramatric search to Grid for page caching | 2
16 | Store API data in cache for Grid component | 2
17 | Retrieve cached API data with Grid initial rendering when and also the user revisits to Grid component. | 2
18 | Store user interactions Width change of Grid component in Redux. | 0.5
19 | Retrieve cached interactions for column width when the user revisits to Grid component. | 0.5
20 | Store user interactions filter change of Grid component in Redux. | 0.5
21 | Retrieve cached interactions for column filter when the user revisits to Grid component. | 0.5
22 | Store user interactions Sorting change of Grid component in Redux. | 0.5
23 | Retrieve cached interactions for column Sorting when the user revisits to Grid component. | 0.5
24 | Store user interactions pagination change of Grid component in Redux. | 0.5
25 | Retrieve cached interactions for pagination when the user revisits to Grid component. | 0.5
26 | Store user interactions row selection of Grid component in Redux. | 0.5
27 | Retrieve cached interactions for row selection when the user revisits to Grid component. | 0.5
28 | Store user interactions of applied save filter of Grid component in Redux. | 0.5
29 | Retrieve cached interactions of applied save filter when the user revisits to Grid component. | 0.5

## 13. Parametric Search Component
HLP Track no.
HLP Type | Parametric Search Component Caching
HLP Description
Track | Item Description | Dev PDs | Priority | Execution Owner / Item Owner | Dev Owner | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
| Implement the paramatric search component from Base component and create a paramatric search component v2 component in UX Framework with Popup | 5
| Add TextField Renderer | 1
| Add Dropdown Renderer | 1
| Operator Feature Support like e.g. Contains, Starts With, Ends With | 3
| Save a filter | 2
| Edit a filter | 1
| Delete a filter | 1
| Default filter | 1

## Target Component
Target Component | Features
Avatar
Avatar Group
Badge
Button
Checkbox
CheckboxGroup
Chip
Content Switcher
Date -> Advance Date Picker
Date -> Calendar
Date -> Range Date Picker
Date -> Rolling Date Picker
Date -> Single Date Picker
DatePicker
DatePickerV1
Divider
Dropdown
Dropdown Menu
Grid
Inline Editor
Input Slider
Input Stepper
Input Text Field
Link
RadioButton
RadioButtonGroup
Search
TextArea
Time Picker
Toggle Switch
Tooltip
Typography
Accordion
Banner
Breadcrumbs
Card
Column Organiser
Dialog
EmptyAndError
ErrorBoundary
File Uploader
KeyValuePair
L2 Footer
L2 Header
Loader
Modal
Pagination
Picklist
Progress Bar
RichTextEditor
RuleBuilder
RuleBuilderV2
RuleViewer
SummaryGrid
Toast Notification
Vertical Tabs
Wizard
WorkFlow Card
Workflow Progress
AccordionForm
Bento
Comments
DocumentViewer
Drawer
Email - > Email Listing
Email -> Email Rule Viewer
Email -> Email Thread
Email -> Email Composer
Email -> Email Menu
Global Footer
Global Header
Grid + Crud
GroupActionProgressBar
ImageViewer
List View
MentionsInput
Navigation -> Primary
Nabigation-> Secondary
Navigation ->Tertiary
NotificationPanel
Page Header
Panel
Parametric Search
PDFViewer
Sort Panel
TiffViewer
TransformationGrid
Tree

## POC (hidden)
HLP Track no. | New Architecture For Components with All latest Libs
HLP Type
HLP Description
Track | Item Description | Dev PDs | Priority | Execution Owner / Item Owner | Dev Owner | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
1 | Add Monorepo and do initial commit to a feature branch with Node JS v23 |  |  |  |  | Need Naveens help on Repo creation with naming convention | [6 empty] | in-progress | 50
2 | Add and Configure Storybook Latest version | [11 empty] | Not Started
3 | Add React Material UI v7 and configure the themes |  |  |  |  | We have successfully tested the button component of MUI v7 in our current version of UX framework locally, and it is working fine. The next step is to test the build and published version of the new component library/framework version in the UX framework. We used Node.js 23, React 18, React MUI v7, along with other latest dependent libraries. Additionally, we conducted a POC with React 19, but encountered compatibility issues with the current UX framework. Therefore, supporting backward compatibility with React 19 in our UX framework is proving to be difficult and complex. |  |  |  | 2025-05-07 |  |  | in-progress | 50
4 | Create a basic Tab component with React MUI v7 and publish the build with version | [8 empty] | 2025-05-02 |  |  | in-progress | 30
5 | Use the same version in UX Framework and test all feature of Tab is working fine | [8 empty] | 2025-05-02 |  |  | Not Started
6 | Add Redux Toolkit and configure the provider and export it for the further use | [8 empty] | 2025-05-07 |  |  | Not Started
7 | Use the Redux Toolkit Provider in UX Framework and provide the context to Tabs component | [8 empty] | 2025-05-07 |  |  | Not Started
8 | Tabs component should default store it's state in Redux | [8 empty] | 2025-05-07 |  |  | Not Started
9
10

## Temp (hidden)
Initial Turborepo with Monorepo Setup and Codebase Structure Setup Eslint:- To use eslint in project setup for code quality and linting Setup Prettier:- To use prettier in project setup for code formatting Setup Husky:- To use husky in project setup for git hooks Setup Lint Staged:- To use lint-staged in project setup for running linters on pre-commit Setup Commitlint:- To use commitlint in project setup for enforcing conventional commit messages Setup Commitizen:- To use commitizen in project setup for creating conventional commits easily Jest with React Testing Lib for Unit testing with cypress for E2E testing Material UI Config:- To use Material UI components in the project setup for UI consistency and design with configuration add MUI theme configuration Material UI Components:- Add atom components like Button, Input, etc. using Material UI for consistent UI design Required Components for Grid and Table:- Add atom components like Button, Input, etc. using Material UI for grid and table components Redux Toolkit Setup:- To use Redux Toolkit in the project setup for state management API middleware:- Use Redux Toolkit query for API middleware and caching data CI/CD Setup:- Add CI and CD setup including version Management and changelog publication Performance monitoring:- Add Google lighthouse and other React performance tooling to validate the performance before code merge including bundle size Documentation:- Add Storybook and Docusaurus for documentation
Add feature to enable v2 grid with a flag from DSL | 1
Integrate API | 1
Add Boolean Display Renderer for page caching | 1
Add DateTime Display Renderer for page caching | 1
Add Text Display Renderers for page caching | 1
Add sort page caching feature | 1
Add search page caching feature | 2
Add column search page caching feature | 2
Add saved search page caching feature | 5
Add refresh button click page caching feature | 1
Add or clone export feature for page caching | 1
Add or clone Pagination features for page caching | 3
Add or clone Bulk Action Feature for page caching | 2
Add or clone and integrate paramatric search to Grid for page caching | 2
Store API data in cache for Grid component | 2
Retrieve cached API data with Grid initial rendering when and also the user revisits to Grid component. | 2
Store user interactions Width change of Grid component in Redux. | 0.5
Retrieve cached interactions for column width when the user revisits to Grid component. | 0.5
Store user interactions filter change of Grid component in Redux. | 0.5
Retrieve cached interactions for column filter when the user revisits to Grid component. | 0.5
Store user interactions Sorting change of Grid component in Redux. | 0.5
Retrieve cached interactions for column Sorting when the user revisits to Grid component. | 0.5
Store user interactions pagination change of Grid component in Redux. | 0.5
Retrieve cached interactions for pagination when the user revisits to Grid component. | 0.5
Store user interactions row selection of Grid component in Redux. | 0.5
Retrieve cached interactions for row selection when the user revisits to Grid component. | 0.5
Store user interactions of applied save filter of Grid component in Redux. | 0.5
Retrieve cached interactions of applied save filter when the user revisits to Grid component. | 0.5
Use Redux to store API responses. |  | 2
Add a timestamp to cached data for expiration logic. |  | 1
Implement a middleware to check the cache before making API calls. |  | 1
Define rules for when cached data should be invalidated (e.g., flag based using DSL, time-based expiration, manual triggers). |  | 2
Add page context to Redux Store and keep it while navigating between pages |  | 1
Add prev page id/key to the next visiting page for reference to clean or refresh the data when needed |  | 1
Add logic to listen to DSL flags for specific data to refresh when needed |  | 1
Enhance the user experience by implementing background data refresh. For example, when a user transitions from a User Listing page to KVP page and modifies data, upon receiving a successful 200 HTTP response, the Listing page's grid data will be automatically refreshed in the background. This ensures data consistency and a smooth, cached page experience. |  | 3
Implement error handling in the API cache middleware |  | 1
Dev testing for all possible scenarios of the impact |  | 3

## UX Framework Changes (hidden)
HLP Track no. | UX Framework Changes
HLP Type
HLP Description
Track | Item Description | Priority | Execution Owner / Item Owner | Dev Owner | Dev PDs | Comments | QA Owner | QA PDs | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Percent Complete
Fix data flow logic (e.g. API Data and User Interaction Data) in framework for caching
Add new Redux states to store user interaction like e.g. Width change, filter and sort in Grid
Create a utility action which can take payload of interactions to store it in page context
Update or Refactor component specific (Ex:- Grid) to put them in Page context
Create a utility action to reset the cached API data in page context for the component with component URN
Dev testing for all possible scenarios of the impact